## Sheet1
North Wales Intermittent and Capital Maintenance Programme 2019/20
FRMS code (FR/**/S***) | FRMS name | Local Authority | Catchment Flood Management Plan (CFMP) name | Shorline Management Plan (SMP) name | Job name | Description of work | NGR | Primary purpose | Secondary purpose | Asset type | Q1 work planned (%) | Q2 work planned (%) | Q3 work planned (%) | Q4 work planned (%)
FR/18/S076 | Lower Conwy | Conwy CBC | Conwy and Clwyd |  | Afon conwy right embankment Tan Lan | Clearing fallen trees from embankment near Maenan Abbey | SH7856165742 - SH7842865784 | Flood Risk | H&S | Embankment |  |  | 50% | 50%
FR/18/S076 | Lower Conwy | Conwy CBC | Conwy and Clwyd |  | Whitebarn Old embankment | Gorse clearing, erosion repairs, installing new stiles | SH7851563521 - SH7921862209 | Flood Risk | Legal - Reservoir Act 1975 compliance | Embankment | 25% | 50% | 25%
FR/18/S072 | Aber & Ddu | Gwynedd Council | North West Wales | West of Wales SMP | Spinnies outfall repairs | Replacing headwall, wingwalls & installing new eel-friendly flap. | SH 61220 72248 | Flood risk | Environmental | Outfall | 100%
FR/18/S071 | Gwyrfai & Seoint | Gwynedd Council | North West Wales |  | Ffos Llyn Bogelyn (r/b) embankment | Raising embankment to design crest level | SH 55297 62517 | Flood Risk | Flood risk | Embankment |  | 100%
FR/18/S074 | Wydden & Ganol | Conwy CBC | Conwy and Clwyd |  | Afon Ganol West tree work | Pollarding willows at Mochdre Ind. Estate. | SH 82128 78445 - SH 81766 78003 | Flood Risk | H&S | Open Channel |  |  | 50% | 50%
FR/18/S078 | Upper Conwy | Conwy CBC | Conwy and Clwyd |  | Dolwyddelan drainage scheme | Installing french drain with outfall at Dolwyddelan | SH 73586 52189 | Flood Risk |  | High ground | 100%
FR/18/S076 | Lower Conwy | Conwy CBC | Conwy and Clwyd |  | Incident exercises | Erecting and testing barriers in Llanrwst | SH7992461483 & SH7987061518 | Flood Risk | H&S | Temporary Barriers | 25% | 25% | 25% | 25%
FR/18/S075 | Dulas | Conwy CBC | Conwy and Clwyd |  | Dulas left bank u/s of railway | Raising embankment to design crest level | SH9076278462 | Flood Risk |  | Embankment |  | 100%
FR/18/S027 | Rossett | Wrexham | 9 Chester |  | Almere repairs | Minor repairs to flood walls and embankment | SJ3875756657 | Flood Risk |  | Embankment | 25% | 50% | 25%
FR/18/S022 | Mold & Pontblyddyn | Flintshire | 9 Chester |  | Raikes Lane, Mold repairs | Minor reparis to flood wall, fence and embankment | SJ2413964667 | Flood Risk |  | Wall | 25% | 50% | 25%
FR/18/S015 | Queensferry H Ferry Balderton | Flintshire | 9 Chester |  | Hawarden embankment | Topping up of embankment | SJ3288968208 | Flood Risk | H&S | Emabankment | 25% | 50% | 25%
FR/18/S083 | Soch | Gwynedd Council | North West Wales |  | Afon Daron erosion repairs | Channel side and flood wall scour repairs including boulder and rock roll replacement | SH1740426456 | Flood Risk |  | Wall |  | 50% | 50%
FR/18/S096 | Dysynni | Gwynedd Council | North West Wales | West of Wales SMP | Afon Dysynni conveyance | Deshoal to the river mouth to allow better Broadwater drainage | SH5641003131 | Flood Risk | IDD | Open Channel |  |  | 100%
FR/18/S092 | Dolgellau & Fairbourne | Gwynedd Council | North West Wales |  | Incident exercises | Operating flood gates and installing barriers in Dolgellau and Fairbourne | SH7303317908 and SH6128113063 | Flood Risk | H&S | Temporary Barriers | 25% | 25% | 25% | 25%
FR/18/S043 | Gele North | Conwy CBC | North East Wales |  | Fyynnon Y Ddol public safety fencing | Remove existing fencing and replace with paladine fencing | SH9960479571 | H&S |  | High ground |  | 100%
FR/18/S047 | St Asaph | Denbighshire CC | North East Wales |  | The Retreat flood embankment | Remove vegetation and carry out repairs to the flood embankment | SJ0327375534 | Flood Risk |  | Embankment |  | 50% | 50%
FR/18/SO86 | Glaslyn & Llanfrothen | Gwynedd Council | North West Wales |  | Cob Crwn embankment | Carry out second year of a Glendale tree management plan | SH5717138989 - SH5727238591 | Flood Risk |  | Embankment |  |  | 50% | 50%
FR/18/SO84 | Rhyd Hir & Erch | Gwynedd Council | North West Wales |  | Embankment adjacent to Pwllheli flood wall | Widen embankment to allow routine maintenance / inspections | SH3733134797 - SH3727634760 | Flood Risk | Legal - Reservoir Act 1975 compliance | Embankment |  |  | 50% | 50%
Note on A1: Kelland, Richard: